WESTERN PACIFIC UNIVERSITY

CMN224 / CMP224 Software Engineering — Week 3

# Lab 3: Lifecycle Selection & Increment Plan

Formative (ungraded) · Moodle-enabled · output feeds Task 2 Part 2 directly

| Item | Details |
| --- | --- |
| Linked to | Week 3 lecture — Software Process Models (ULO2, ULO3) |
| Work mode | Individually, on the SAME client scenario you chose for Task 2 |
| Time | About 90 minutes |
| Submission | Completed worksheet uploaded to Moodle AND committed to week03/ in your Git portfolio |
| Why it matters | Section C of this worksheet is a first draft of Task 2 section 2.3 (work schedule). Do it properly now and Week 8 gets much easier. |

## Purpose

In the lecture you met six ways to organise the same four activities, and six questions that decide which one fits. Now you apply that decision to a real client — yours. There is no single correct model; the marks in Task 2 (and the exams) come from the quality of your justification.

## Part A — Apply the six selection questions (30 min)

For each question, answer for YOUR client scenario (Kina Ridge Primary School or Waghi Valley Produce Cooperative) and say what it pushes you toward.

| # | Selection question | Your answer for this client | Pushes toward… |
| --- | --- | --- | --- |
| 1 | How well understood are the requirements? | Basic needs such as student records, attendance, and reporting, | Incremental/Agile |
| 2 | Can the client engage continuously? | The school administration can provide feedback during the term; it maybe varies because of teaching and administrative duties | Incremental / Agile |
| 3 | What does the contract or funding demand? | The school expects clear milestones and evidence of progress before accepting the final system. | Incremental with phase reviews |
| 4 | How big is the team, and where is it? | The development team is small and may not always be on-site. Communication will mainly occur through meetings and messaging. | Incremental |
| 5 | What is the cost of failure? | Loss of student records or inaccurate reports would be serious, but the project is not life critical. | Structured testing within Incremental |
| 6 | How fast must value appear for this client? | The school would benefit from using basic record management as soon as possible instead of waiting for the complete product. | Incremental / Agile |

## Part B — Choose and justify (15 min)

Chosen lifecycle: Incremental Development with Agile feedback cycles (may be a blend — say so explicitly)

In 150–200 words, justify the choice using your Part A answers. Name at least one factor that argues AGAINST your choice, and say how you will manage it.

The most suitable lifecycle for Kina Ridge Primary School is an Incremental Development approach supported by Agile feedback sessions. The school's core requirements, such as student registration, attendance tracking, and report generation, are generally understood, but some details are likely to change after staff members see and use the system. Delivering the software in increments allows the client to receive useful functionality early while providing feedback that improves later releases.

Continuous client involvement is possible because school administrators and teachers can review each increment and suggest improvements. This reduces the risk of developing features that do not match actual school processes. Incremental delivery also provides clear milestones that can be reported to school management and funding stakeholders.

One factor that argues against this approach is that school staff may not always be available for frequent reviews due to teaching schedules and administrative workloads. This risk will be managed by scheduling review meetings at agreed times and documenting feedback carefully so that development can continue even when direct input is temporarily unavailable.

Blends are professional, not a cop-out. "Incremental delivery internally, phase milestones reported to the board" is a legitimate and common answer in PNG work — provided you explain how the two fit together.

## Part C — Plan three increments (35 min)

Split your client's system into three increments. Increment 1 must be genuinely usable on its own — something the client could put to work the day you hand it over.

| Increment | What it delivers | Why THIS order (risk or value?) | Rough duration & why |
| --- | --- | --- | --- |
| 1 | Student registration and record management | Highest business value because the school can immediately store and manage student information. | 3 weeks. Core database and user interface must be established first. |
| 2 | Attendance tracking and class management | Builds on student records and helps teachers monitor attendance daily. | 2 weeks. Uses data structures created in Increment 1. |
| 3 | Reporting, analytics, and printable summaries | Provides management information after student and attendance data are available. | 2 weeks. Depends on data collected from earlier increments. |

### C4. Delivery-condition check

For each increment, note one PNG delivery condition that affects when or how you can deliver it (client travel, power, connectivity, harvest or school-term timing, committee approval cycles).

Condition notes

School holidays and staff availability may affect requirements gathering and training.

Unreliable internet or power interruptions may affect testing and deployment.

## Part D — Reflect (10 min)

- If the client suddenly demanded ALL three increments by the same original deadline, which corner of the dependency triangle would you push back on, and what exactly would you say to them?

- Which of your three increments is most likely to change after the client sees increment 1? What does that tell you about how firmly to specify it now?

Your answers

I would say to maintain the agreed quality and deadline, we would need to reduce the amount of functionality included in the final release. We can prioritise the most important features first and schedule less critical features for a later update. This ensures the system remains reliable and useful rather than rushing all features and risking defects."

Increment 3 (Reporting and Analytics) is most likely to change because users often discover new reporting needs after they start entering and using real data. This means the reporting requirements should be specified at a high level initially and refined through feedback after Increment 1 has been deployed and tested in actual school operations.

## Submitting

- Save as Lab3_<YourName>.docx and upload to Moodle → Week 3 → Lab 3.

- Copy it into week03/ in your portfolio and commit:

git add week03/ && git commit -m "Add Lab 3 lifecycle selection and increment plan"

- Keep it open when you start Task 2 Part 2 — Parts B and C become sections 2.3 and 2.4.